## Sheet1
Đề xuất tài trợ: Chuyên gia giỏi nước ngoài - Dự án "Tiếp thu và làm chủ công nghệ dự báo bão hạn mùa bằng mô hình động lực, phục vụ công tác bảo đảm an toàn cho các hoạt động kinh tế - xã hội và an ninh trên khu vực Biển Đông - Việt Nam" Đơn vị đề xuất: Trường Đại học Khoa học Tự nhiên
No | Activities | Time of implementation
I | WP1: Kick-off workshop, construction and development of pre- and post-processing modules (PrePos) | 04/2017-12/2017
1.1 | Project kick-off workshop and discussions on the detailed project plans Duration: 1 day Expected participants: 70, including national and international experts, researchers from related institutions Location: Hanoi | 23/11/2017
1.2 | Visiting of three CSIRO's experts for attending the "Kick-off workshop, construction and development of pre- and post-processing modules (PrePos)" and working with Vietnamese scientists on the project plans Duration of working time: 8 days (excluding travel time) Note: Time schedule for visiting of experts might be different depending on the activities. | 20-27/11/2017
II | WP2: Developing the coupled AOGCM model system for VES and Vietnam region | 07/2017-07/2018
2.1 | Visiting of three CSIRO's experts for working with Vietnamese scientists on the implementation of AOGCM for Vietnam and attending the workshop on the selection of AOGCM configuration for Vietnam East Sea (VES), such as domain choices, resolutions, physical parameterization schemes, etc Duration of working time: 8 days (excluding travel time) Note: Time schedule for visiting of experts might be different depending on the activities. | 07/2018
2.2 | Workshop on the selection of AOGCM configuration for Vietnam East Sea (VES), such as domain choices, resolutions, physical parameterization schemes, etc Thời gian: 2 ngày trong khoảng tháng 7-10/2017 Duration: 1 day Expected participants: 70, including national and international experts, researchers from related institutions Location: Hanoi | 07/2018
III | WP3: Developing the tropical cyclone detection scheme (TD-Detect) from AOGCM's outputs | 07/2017-03/2018
IV | WP4: Building and developing the ensemble methods of the modeled TCs (TC-Ens) | 10/2017-06/2018
4.1 | Visiting of three CSIRO's experts for working with Vietnamese scientists on the ensemble methods of the seasonal TC forecast Duration of working time: 8 days (excluding travel time) Note: Time schedule for visiting of experts might be different depending on the activities. | 12/2018-01/2019
4.2 | Workshop on the ensemble forecast applied to the seasonal TC forecasting Duration: 2 day Expected participants: 70, including national and international experts, researchers from related institutions Location: Hanoi | 12/2018-01/2019
V | WP5: Building and developing the auto-run system for operational forecast (AUTO-Ope) | 10/2018-03/2019
VI | WP6: Experiments of the seasonal TC simulation and prediction using STCPS and verification | 10/2017-12/2018
VII | WP7: Human capacity building and technology transferring | 04/2017-03/2019
7.1 | Four (4) young Vietnamese staffs will be trained at CSIRO on the 1) AOGCM model system, 2) Pre-Pos Processing technology, 3) TC detection techniques, and 4) TC ensemble forecasting. Duration: Three and half months (107 days) | 03-06/2018
7.2 | Three (3) Vietnamese scientists will visit and work with CSIRO's experts on the 1) Operational Auto-run system, and 2) Implementation of the AOGCM system for VES and Vietnam region Duration: 4 weeks (30 days) | 03-06/2018
7.3 | Project final workshop and project output launching Duration: 1 day Expected participants: 70, including national and international experts, researchers from related institutions Location: Hanoi | 05/2019
7.4 | Visiting of three CSIRO's experts for attending the final workshop and working on the technology transfer and closing project Duration of working time: 8 days (excluding travel time) Note: Time schedule for visiting of experts might be different depending on the activities. | 05/2019
VIII | WP8: Buy and upgrade equipment (HPC) | 12/2017
8.1 | Buying the High Performance Computing and Storage Systems (HPC) to be used to carry out the experimental simulation and prediction of the STCPS during implementing the project. This HPC will also be used for operational run after closing project